## Sheet1
External Transport Servies
Key | Route/Theme | Action | Partners | Date | Progress | Objective/ Purpose | Target Contribution
APS1 | Scottish Lifeline Routes - Aberdeen, Edinburgh, Glasgow, Inverness | Work with existing air operators to seek improvements to existing services to UK mainland | ZetTrans (TOM) | Ongoing |  | Improved frequency, cost, routes, timetables /affordable fares / improved customer care of external air services, ECON 1-7, SIA 1-5, ENV 2 | KPI1, 4. M1, M2c, M3, M5b
APS2 | Scottish Lifeline Routes - Aberdeen, Edinburgh, Glasgow, Inverness | Support continuation and development of Air Discount Scheme, including involvement in future evaluations | Scottish Government, ZetTrans (TOM), HITRANS, Nestrans | Ongoing |  | Continuation and development of scheme, including extension to visitors. Improve cost of external air services. ECON 2, SIA 2 | M1
APS3 | Scottish Lifeline Routes - Aberdeen, Edinburgh, Glasgow, Inverness | Support the exploration of PSOs for lifeline flights | ZetTrans (HT), HITRANS | Summer 09 |  | Improve cost of external air services. ECON 2, SIA 2 | M1
APS4 | Sumburgh Airport | Support HIAL's development of Sumburgh Airport, such as improving operations, operating in full accordance with relevant legislation, including safety and security, DDA etc. and encourage improvements in fuel efficiency | HIAL, ZetTrans (HT) | Ongoing |  | Reduce impacts of climate change and of fuel provide increases. ECON 3, ENV 1, ENV 2 Access for disbaled people. SIA 2, SIA 5 Safety. SAFE 1 Maintain, and, where possible, improve external lifeline services. ECON 1-7, SIA 1-3, | KPI4, M3
APS5 | UK, Continental Europe and Scandanavian routes | Work with partners in order to encourage other operators, or other routes to be developed from Sumburgh | ZetTrans (HT), Government, Enterprise Agencies, Tourism Agencies, HIAL | Ongoing |  | Improved access to and from Shetland. ECON 6 | KPI4, M3
APS7 | UK Gateway Airports | Support for other RTPs in their development of effective transport interchanges and public transport services and facilites at UK gateway airports (Aberdeen, Inverness, Edinburgh, Glasgow) | ZetTrans (HT), Nestrans, HITRANS, other stakeholders, UK gateway airports | Ongoing |  | Improve public transport access to Sumburgh. INT 1, INT 2 | M8
AFS1 | Air Freight | Supports continued provision of existing air freight services on commercial basis. | ZetTrans (HT) | No action required |  | - | -
UKF1 | Northern Isles Lifeline Route | Continue to lobby for improvements: cabin availability, timetabling suits needs of Shetland's population, apppropriate and affordable freight and livestock arrangements. And encourage service to be delivered in full accordance with relevant safety and security regulations, DDA and encourage improvements in fuel efficiency. | ZetTrans (TOM) | Ongoing |  | Reduce impacts of climate change and of fuel provide increases. ECON 3, ENV 1, ENV 2 Access for disbaled people on external ferries. SIA 2, SIA 5 Safety. SAFE 1 Maintain, and, where possible, improve external lifeline ferry. ECON 1-7, SIA 1-3, | KPI1b, KPI4e, M1
UKF2 | Northern Isles Lifeline Route | Consider options for future development of Northern Isles Ferry service, including alternative vessel options and route configurations. Building on work undertaken through the Northern Maritime Corridor Study and accounting for passengers, freight, livestock and elements of economy | ZetTrans (TOM), HITRANS, Nestrans | Awaiting outcome of OD study |  | Maintain, and, where possible, improve external lifeline ferry. ECON 1-7, SIA 1-3, | M2, M3, M7
UKF3 | Aberdeen Harbour | Encourage delivery of improved transport integration opportunities and facilites, considering passengers, freight, livestock | ZetTrans (HT), Nestrans, other stakeholders | Initial Meeting end sept |  | Improve access to ferry terminal. INT 3
UKF4 | External Frieght | Lobby for continued freight subsidy and support development of subsidy for Lo-Lo freight | ZetTrans (TOM) | Ongoing |  | Optimise freight shippment and affordability. SIA 1, INT 4 | M1
ESF1 | European/Scandinavian Ferry Link | Support investigation of potential | ZetTrans (TOM) | Operating 2009 |  | Widen geographic access to and from Shetland. ECON 1-2, ECON 4, ECON 6-7 | KPI1, KPI4, M1, M2, M3 | Indicators?
PH1 | Ports and Harbours | Support ongoing strategic development of Shetland's Ports and associated facilities, including consideration of the most appropraite model of provision of the services and facilities, particularly in light of Shetland's changing economic opporutnities (Lerwick Port Authority, Sullom Voe, Scalloway Harbour), including access to HGVs | ZetTrans (TOM) | TBC |  | Optimise freight and passenger shipment by ferry, from and to Shetland. ECON 1, ECON 4, ECON 6, ECON 7, SIA 1 | KPI1, KPI4, M2, M3
PH2 | Ports and Harbours | Support Aberdeen Harbour Board's ongoing work to improve the operational reliabiltiy of the harbour and therefore performance and capacity of current Northern Isles service | Nestrans, ZetTrans (HT) | Dependent on Nestrans |  | Optimise freight and passenger shipment by ferry, from and to Shetland. ECON 1, ECON 4, ECON 6, ECON 7, SIA 1 | KPI1, KPI4, M2, M3
BF1 | Bulk Freight | Lobby for appropriate subsidy arrangements to support bulk freight movements to and from Shetland | ZetTrans (TOM), Scottish Government
EX1 | All External Transport | Establish and maintain consultation forum for customers and industry groups, to meet regularly with operator to discuss operational issues | ZetTrans (TOM) | 2007-10-01
EX2 | All External Transport | Meet regularly with HITRANS and Nestrans to discuss specification and policy issues regarding service | ZetTrans (TOM), HITRANS, Nestrans | 2007-11-01
EX3 | All External Transport | Proactive approach to monitoring of external air services, focusing on service levels, service reliablity and fare levels. | ZetTrans (PSM) | 2008-06-01 |  | Monitoring. ECON 1, ECON 2 | KPI1, M1, M3
EX4 | All External Transport | Proactive approach to monitoring of external ferry services, focusing on service reliablity cabin and vehicle availabilitiy, freight, livestock issues, fare levels and customer care. | ZetTrans (PSM), accessing data from Scottish Government | 2008-06-01 |  | Monitoring. ECON 1, ECON 2 | KPI1, M1, M2a, M3
EX5 | All External Transport | Undertake an external links Origin Destination Survey (inbound and outbound passenger, freight and livestock movements, by ferry and air and current non-travellers) | ZetTrans (PSM), HITRANS, Nestrans | 2008-11-01 |  | Maintain, and, where possible, improve external links. ECON 1-7, SIA 1-3, | M1-3, M5, M7
Inter-island Links
FL1 | Fixed Links | Developing fixed link strategy for Shetland | ZetTrans (HT) |  |  | Establish principles for long-term sustainability of transport links. ECON 1, ECON 2, ECON 5, ECON 7, SIA 1-5 | M2b
FL2 | Fixed Links | Tunnelling Standards and Specifications Study | ZetTrans (HT), Roads
IIF1 | Unst/Fetlar Links | Bluemull STAG for sustainable transport link | ZetTrans (PSM) | 2008-08-01 | STAG 2 reporting early August | Long term sustainability of transport infrastructure. ECON 1, 4, 5, SIA 1-5 | M2b
IIF2 | Unst/Fetlar Links | Fetlar Breakwater | ZetTrans (PSM), Ports and Harbours, Capital Programmes Service, EDU | 2007-11-01 | Awaiting Capital Funding | Assess whether improvements can be justified to the existing service levels. ECON 1 | KPI1d
IIF3 | Unst/Fetlar Links (if fixed link not viable short to medium term) | Replace existing terminals at Gutcher and Belmont | ZetTrans (HT) | Summer 08 |  | Maintain current service. ECON 1, SIA 1, ENV 4, 5, 7, 9, SAFE 1 | M6a
IIF4 | Unst/Fetlar Links (if fixed link not viable short to medium term) | Within terminal redevelopment, consider alternative overnight berthing facilites and locations | ZetTrans (HT) | Align with project development |  | Maintain current service. ECON 1, SIA 1, SAFE 1 | M6a
IIF5 | Unst/Fetlar Links (if fixed link not viable short to medium term) | Replace MV Fivla and MV Geira | ZetTrans (HT) | Align with project development |  | Maintain current service. ECON 1, SIA 1, ENV 4, 5, 7, 9, SAFE 1 | M6a
IIF6 | Bressay Link | Bressay Link STAG assessment to examine future options for link to Bressay, and implementation of findings | ZetTrans (HT) | 2008-03-01 |  | Establish principles for long-term sustainability of transport links. ECON 1, ECON 2, ECON 5, ECON 7, SIA 1-5 | M2b
IIF7 | Whalsay Link | STAG 2 - Appraisal of Options and implementation of options | ZetTrans (HT) | 2007-12-01 |  | Long term sustainability of transport infrastructure. ECON 1, 4, 5, SIA 1-5 | M2b
IIF1,6,7 | 3 Links Strategy | Implementation Plan | ZetTrans (HT) | 2009-01-01
II8 | Fair Isle | Commission replacement of MV Good Shepherd, and berth - Outer Isles STAG | ZetTrans (PSM) | 2012-17 |  | Establish principles for long-term sustainability of transport links. ECON 1, ECON 2, ECON 5, ECON 7, SIA 1-5 | KPI1d, M1a
II9 | Fair Isle | Option to undertake additional sailing, autumn shoulder period - Outer Isles STAG | ZetTrans (PSM) |  |  | Improved access to and from Isle. ECON 4, SIA 1, 4 | KPI1d, KPI4c, M2b
II10 | Foula | Monitor and review contract | ZetTrans (PSM) | For 2010 |  | Maintain sustainable ferry links. ECON 1, ECON 2, ECON 5, ECON 7, SIA 1-5 | KPI1d, M1a
II11 | Papa Stour | Timetable Options: consider additional return route (partially offset by withdrawing scheduled air service?) - Outer Isles STAG | ZetTrans (PSM) |  |  | Maintain sustainable ferry links. ECON 1, ECON 2, ECON 5, ECON 7, SIA 1-5 | Links with air , M1a, M2
II12 | Papa Stour | Consider MV Thora instead of MV Snolda during summer - Outer Isles STAG | ZetTrans (PSM) |  |  | Maintain sustainable ferry links. ECON 1, ECON 2, ECON 5, ECON 7, SIA 1-5 | KPI1d, M1a
II13 | Skerries | Study collating evidence reSouth Mouth | ZetTrans (PSM) | 2008-02-01 |  | Maintain sustainable ferry links. ECON 1, ECON 2, ECON 5, ECON 7, SIA 1-5 | KPI1d
II14 | Skerries | Options for revised service: Vidlin based service, new freight delivery structure, improved public transport connections between Lerwick and Vidlin - Outer Isles STAG | ZetTrans (PSM) |  |  | Maintain sustainable ferry links. ECON 1, ECON 2, ECON 5, ECON 7, SIA 1-5 | KPI1d, M1a
FOP1 | Ferries, Operational | Monitor whether service subject to competitive tendering, re European legislation | ZetTrans (TOM) | Ongoing |  | Legal ferry service. ECON 1
FOP2 | Ferries, Operational | Continue to ensure ferries operate in accordance with DDA | ZetTrans (TOM) |  |  | Access for disbaled people on internal ferries. SIA 2, SIA 5 | M4a
FOP3 | Ferries, Operational | Continue to ensure operate in compliance with national safety and security regulations | ZetTrans (TOM) |  |  | Safety. SAFE 1 | M6a
FOP4 | Fare structures | Develop Fare Structure appropriate to Shetland, including consideration of options for generating additional utilisation and revenue and effectiveness of Bluemull fares policy | ZetTrans (HT) | To be completed by end March 2009 |  | Robust cost-benefit of fares. ECON 1, 2, 4, 5, SIA 1, 2, 5 | M1a
FOP5 | Fare structures | Lobby for national concessionary fares scheme to extend to inter-island ferries | ZetTrans (HT), HITRANS, Nestrans |  |  | National equality. ECON 7, SIA 5 | KPI4c
FOP6 | Level of service | Alternative frequencies to better match supply with demand | ZetTrans (TOM) |  |  | Efficient and effective service. ECON 1, 2, 3, 4, 5, 7, SIA 1, ENV 1 | KPI3, M2b, M8b
FOP7 | Level of service | Alternatives to 24 hour manning and operation on Yell Sound | ZetTrans (TOM) |  |  | Efficient and effective service. ECON 1, 2, 3, 4, 5, 7, SIA 1, ENV 1 | KPI3, M2b, M8b
FOP8 | Level of service | Alternative vessel deployment patterns, including Skerries service | ZetTrans (TOM) |  |  | Efficient and effective service. ECON 1, 2, 3, 4, 5, 7, SIA 1, ENV 1 | KPI3, M2b, M8b
FOP9 | Community Hires | Support community ferry hires system, further develop and improve flexiblity of system | ZetTrans (TOM) |  |  | Efficient and effective service. ECON 1, 2, 3, 4, 5, 7, SIA 1, 5, ENV 1 | KPI3, M2b, M8b
FOP10 | Fuel efficiency | Emphasis on fuel efficiency on purchase of future vessels | ZetTrans (TOM) |  |  | Reduce impacts of climate change and of fuel provide increases. ECON 3, ENV 1, ENV 2 | KPI3
FOP11 | Bookings | Improve booking and ticketing arrangements, including integrated ticketing | ZetTrans (PSM)
FOP12 | Signs | Improve use of Variable Messaging Signs | ZetTrans (PSM)
FOP13 | Freight service | Ensure ongoing operation and availabiltiy of freight facilities for Fair Isle, Foula, Papa Stour and Skerries | ZetTrans (TOM) |  |  | Optimise freight shippment and affordability. SIA 1, INT 4 | M7
FOP14 | Monitoring of services: usage, bookings etc. | Proactive approach to monitoring of external air services, focusing on service levels, service reliablity and fare levels. | ZetTrans (PSM) | 2008-06-01 |  | Monitoring. ECON 1, ECON 2 | KPI1, M1, M3
IIA1 | Tingwall Airport | Support ongoing operation, as Mainland Hub: maintain airport with facilities for passengers and small parcels, and ongoing operation of individuals airstrips on each of islands | ZetTrans (TOM) |  |  | Efficient and effective service. ECON 1, 2, 3, 4, 5, 7, SIA 1, 3, 5, ENV 1 | KPI1c, KPI4d, M2c, M5a, M8
IIA2 | Unst Airport | Supports interest in re-opening Unst to provide direct chartered air services (private operators) | ZetTrans (TOM) |  |  | Improved access and economic development opportunities. ECON 4, 5, 7, SIA 4 | KPI4d, M2c
IIA3 | Fetlar Air | Supports operation of chartered flights to Fetlar (private operators) | ZetTrans (TOM) |  |  | Improved access and economic development opportunities. ECON 4, 5, 7, SIA 4 | KPI4d, M2c
IIA4 | Fair Isle Air | Supports ongoing development of air services through review of opportunities with 2nd Islander or increased promotion of chartered services for visitors - Outer Isles STAG | ZetTrans (PSM) |  |  | Improved access and economic development opportunities. ECON 4, 5, 7, SIA 4 | KPI4d, M2c
IIA5 | Foula Air | Use review of 2nd aircraft to examine opportunities for 2nd daytrip in winter - Outer Isles STAG | ZetTrans (PSM) |  |  | Improved access and economic development opportunities. ECON 4, 5, 7, SIA 3, 4 | KPI4d, M2c, M5a
II6 | Papa Stour Air | Review scheduled service alongside ferry service patterns review - Outer Isles STAG | ZetTrans (PSM) |  |  | Improved access and economic development opportunities. ECON 4, 5, 7, SIA 3, 4 | KPI4d, M2c, M5a
II7 | Skerries Air | Consider whether need for additional winter service within review of 2nd aircraft | ZetTrans (PSM) |  |  | Improved access and economic development opportunities. ECON 4, 5, 7, SIA 3, 4 | KPI4d, M2c, M5a
II8 | Fares | Review on regular basis | ZetTrans (HT) |  |  | Inclusion. | M1, M2c, M8
II9 | Monitoring | Continued monitoring of operational performance and utilisation of present inter-islands air service. | ZetTrans (PSM) |  |  | Monitoring. ECON 1, ECON 2 | M1, M2c, M8
II10 | Safety | Continue to ensure operated in compliance with applicable national safety and security regulations | ZetTrans (TOM) |  |  | Safety. SAFE 1 | M6b
IIF11 | Partners | Work with Okney to explore opportunities for collaboration | ZetTrans (HT)
Internal Links
WAL1 | Walking | Support Core Paths Plan | ZetTrans (TSO), SIC |  |  | Promote walking as healthy, emission free and social activity. ECON 1, 3, 4, 5, 7, SIA 1, 4, ENV 1, 2, 3, SAFE 1 | KPI3a, KPI4a. KPI6d
WAL2 | Walking | Identify potential locations for new links within communities, or between communities and key facilities, using community consultation | ZetTrans (PSM), Roads, Planning | Ongoing |  | Safe and attractive walking networks within and between settlements, providing access to local facilities. ECON 1, 3, 4, 5, 7, SIA 1, 4, ENV 1, 2, 3, SAFE 1 | KPI3a, KPI4a. KPI6d
CYC1 | Cycling | Secure cycle stands at key locations within main settlements / Inclusion of cycling facilities within workplaces | ZetTrans (PSM), Planning, Roads, Core Paths, NHS |  |  | Safe and attractive cycling networks within and between settlements, providing access to local facilities. ECON 1, 3, 4, 5, 7, SIA 1, 4, ENV 1, 2, 3, SAFE 1 | KPI3a, KPI4a. KPI6d, KPI7
CYC2 | Cycling | Undertake audit of potential cycling opportunities, considering links within and between settlements and other key facilities | ZetTrans (PSM), Planning, Roads, Core Paths, NHS | Ongoing |  | Safe and attractive cycling networks within and between settlements, providing access to local facilities. ECON 1, 3, 4, 5, 7, SIA 1, 4, ENV 1, 2, 3, SAFE 1 | KPI3a, KPI4a. KPI6d
CYC3 | Cycling | Development and promotion of cycling for tourists and leisure purposes: national cycle network, including cycle route guide: cycle hire, repair facilites, on and off road routes, ferry connections | ZetTrans (PSM), Planning, Roads, Core Paths, NHS |  |  | Eco-friendly tourist development. ECON 1, 3, 4, 5, 7, SIA 1, 4, ENV 1, 2, 3, SAFE 1 | KPI3a, KPI4a. KPI6d
PTW1 | Powered Two Wheelers | Consider initatives for improving motorcycle safety (including road maintenance) | ZetTrans (PSM), Northern constabulary | Ongoing |  | Safety. SAFE 1 | KPI7
PTW2 | Powered Two Wheelers | Supports provision of secure parking facilities for motorcyclists in settlements and within staff travel plans (stands) | ZetTrans (PSM) |  |  | Increased use of fuel efficient transport. ECON 1, 3, 4, 5, SIA 4, ENV 1, 2, 7, SAFE 1 | KPI3, KPI6b
PTW3 | Powered Two Wheelers | Promotion of motorcycling for tourists - possible motorcycle route guide detailing appropriate routes | ZetTrans (PSM) |  |  | Tourist development. ECON 1
STR1 | Travel Plans | Actively promote continued development of school travel plans. | SIC Safety and Risk, Active Schools |  |  | Safe journeys to school, promotion of active lifestyles, increased environmental awareness. ECON 1, 4, SIA 4, ENV 1, 2, 3, SAFE 1 | KPI3a, KPI6, KPI7
STR2 | Travel Plans | Support workplace travel plan for SIC/ZetTrans & NHS | ZetTrans, SIC workforce (PSM) | 2008-01-01 01:55 |  | Reduction in car use:Promote flexible working practices, promotion of car-sharing, promotion of walking and cycling between offices, video and teleconferencing. ECON 1, 4, SIA 4, ENV 1, 2, 3, SAFE 1 | KPI3a, KPI6, KPI7
STR4 | Community Travel Plans | Feasiblity study considering development of intiatives to promote more sustainable travel behaviour, informing more specific initatives for implementation | ZetTrans (PSM) |  |  | Promotion of car-sharing, walking and cycling. ECON 1, 4, SIA 4, ENV 1, 2, 3, SAFE 1 | KPI3a, KPI6, KPI7
STR5 | Reducing Emissions | Feasibilty study identifying most effective means of reducing emissions arising from transport in Shetland, informing more specific initiatives for implementation | ZetTrans (PSM) |  |  | Reduction in emissions. ENV 1, 2, 3 | KPI3a, KPI6, KPI7
LRS1 | Road Schemes | Continue to prioritise road improvments using established approach. Promote road improvements for the following purposes: Relatively minor extensions of existng 2-lane road network to provide links to existing settlements; developments in conjunction with large scale housing; footway improvements works within existing settlements; structural improvements to specific stretches of minor roads to reduce long term maintenance burdens; specific junction improvements in response to increased or changing traffic flows | SIC Roads | Ongoing |  | Robust approach to decision-making. ECON 1, 4, 5, SIA 1, 4, ENV 4-9, SAFE 2-6 | KPI2, KPI7
| Two Lane Spine Road Network, firm proposals | Haggersta | SIC Roads | Ongoing |  | Needs-based, safe and reliable road network. ECON 1, 4, 5, SIA 4, ENV 4-9, SAFE 2-6 | KPI2, KPI7
|  | Scord to School, Phase 2 | SIC Roads
|  | Minor extensions of 2 lane road network - spine road | SIC Roads
|  | Improvement of existing roads for maintenance purposes - spine road | SIC Roads | Ongoing
|  | Traffic flows - junctions - spine road | SIC Roads | Ongoing
|  | Oversund | SIC Roads | 2009-04-01
| 2nd tier Links between settlements onto Spine Roads | Mid Yell Phase 1 | SIC Roads | 2009-06-01
|  | Mid Yell Phase 2 | SIC Roads
|  | Minor extensions of 2 lane road network - 2nd tier roads | SIC Roads
|  | Improvement of existing roads for maintenance purposes - 2nd tier | SIC Roads | Ongoing
|  | Traffic flows - junctions - 2nd tier | SIC Roads | Ongoing
| Local Road Network | Papa Stour Road | SIC Roads
|  | Gilbertson Road Reconstruction | SIC Roads | 2008-03-01
|  | Improvement of existing roads for maintenance purposes - local roads | SIC Roads | Ongoing
|  | Large scale housing | SIC Roads | Ongoing
|  | Traffic flows - junctions - local roads | SIC Roads | Ongoing
LRS2 | Biodiversity | Continue to implement roadside bio-diversity action plan during routine maintenance work and road development schemes | SIC Roads | Ongoing |  | Improve bio-diversity of road-side. ENV 6
LRS3 | Landscape and Environment Guide | Best practice design guide for rural roads, to complement landscape and environment | SIC Roads | Ongoing |  | Roads fit within Shetland landscape and environment. ENV 4-8
LRM1 | Road Maintenance and Management | Continue to undertake sructural maintenance, routine maintenance and regular inspections of local road network to maintain value of asset and ensure roads continue to be 'fit for purpose' | SIC Roads | Ongoing |  | Safe and reliable road network. ECON 1, 4, 5, SIA 4, ENV 4-9, SAFE 2-6 | KPI2, KPI7
LRM2 | Road Maintenance and Management | Inspect, assess and maintain all structures in accordance with national Codes of Practice for Bridge Management | SIC Roads | Ongoing |  | Safe and reliable road network. ECON 1, 4, 5, SIA 4, ENV 4-9, SAFE 2-6 | KPI2, KPI7
LRM3 | Road Maintenance and Management | Maintain existing street lighting in accordance with national standards. Includes reducing light pollution and energy consumption by use of modern street lighting & modification of unnecessary or inappropriate lighting. | SIC Roads | Ongoing |  | Safe and reliable road network. ECON 1, 4, 5, SIA 4, ENV 4-9, SAFE 2-6 | KPI2, KPI7
RSF1 | Road Safety | Engineering: Maintain programme of traffic calming, discrete road safety schemes and route action oplans | SIC Roads | Ongoing |  | Deliver of Shetland's Road Safety Plan. SAFE 2, 6 | KPI7
RSF2 | Road Safety | Monitor road traffic accidents by location and crash type to inform development of potential remedial schemes | SIC Roads | Ongoing |  | Reduce road traffic accidents. SAFE 2-6 | KPI7
RSF3 | Road Safety | Encouragement and Education: Initiate specific road safety education campaigns (speeding, seat belt enforcement, mobile phone legislation, drink/drug driving) | SIC Roads | Ongoing |  | Reduce road traffic accidents. SAFE 2-6 | KPI7
RSF4 | Road Safety | Lobby for regular targeted traffic law enforcement campaigns within Shetland | SIC, ZetTrans (PSM) | Ongoing |  | Reduce road traffic accidents and complement RSF3. SAFE 2-6 | KPI7
RRA1 | Risk Assessment and Contingency Planning | Continue to develop risk assessment processes in relation to flooding for local road network and landslips | SIC | Ongoing |  | Risk adversion and adaptation to climate change. ENV 9
RRA2 | Risk Assessment and Contingency Planning | Promote contingency planning for short-term unavailability of key sections of local road network | SIC, ZetTrans (PSM) |  |  | Risk adversion and adaptation to climate change. ENV 9
RWM1 | Winter Maintenance | Develop and implement winter maintenance programme and procedures, prioritising action on most heavily used routes, footways within settlements that link key facilities nad provision of grit bins | SIC | Done |  | Safe access during winter months. SAFE 2 | KPI7
RWM2 | Winter Maintenance | Update policies on regular basis, based on user involvement | SIC | 2009-08-01 |  | Needs-based and safe access during winter months. SAFE 2 | KPI7
PAR1 | Parking | Continue to support existing disc parking system within centre of Lerwick. Continue to monitor provision of on and off street parking in Lerwick, including Holmsgarth ferry terminal and other settlement areas, and consider appropraite solutions to identified problems. | SIC | Ongoing |  | Ensure availability of on and off street parking for short and long-term demands. ECON 1, 4, SAFE 2
PAR2 | Parking | Provide dedicated parking for disabled users | SIC | Ongoing |  | Access for disabled. SIA 5, SAFE 2
PAR3 | Parking | Support maintenance and development of park and ride/ transport interchange facilities at appropraite sites along main road network | SIC, ZetTrans (PSM) | Ongoing |  | Reduce carbon emissions: facilitate car sharing and access to mainline public transport network. ENV 2, SIA 1 | KPI3a
PAR4 | Parking | Support adoption of parking guidance within Local Plan | SIC, ZetTrans (PSM) | Ongoing |  | Ensure availability of on and off street parking for short and long-term demands. ECON 1, 4, SAFE 2
RMN1 | Monitoring | Regular and systematic surveys of road traffic at services of key locations on Shetland's spine road network (loop surveys) | SIC | Ongoing |  | Efficient and effective road system. ECON 1 | KPI4a
RMN2 | Consultation | Regular consulation with respect to local road network issues + surveys | SIC | Ongoing |  | Efficient and effective road system. ECON 1 | KPI2, KPI7
PTS1 | Public Transport Services | Review public transport policy statement - vision and action plan (continue provision of existing mainline public transport services and associated feeder services and trial new or amended service patterns including evening and late night servcies) | ZetTrans (PSM) |  |  | Each mainland community has access to employment and education opportunities within Lerwick. SIA 1-5 | KPI4a and b, KPI5, M1, M5a
PTS2 | Public Transport Services | Integrated PT opportunities, particularly Sumburgh and Holmsgarth | ZetTrans (PSM) |  |  | Each mainland community has access to employment and education opportunities within Lerwick. SIA 1-5 INT | KPI4a and b, KPI5, M1, M5a
PTS3 | Public Transport Services | Stock take of CT/DRT and implementation (Continue to investigate and trial innovative forms of PT delivery) | ZetTrans (PSM) |  |  | Improve service levels, reliabiltiy and efficiency whilst reducing costs. SIA 1-5 | KPI5a, M5a
PTS4 | Public Transport Services | All PT services delivered in accordance with DDA (including information accessible) and in accordance with relevant national and safety legislation | ZetTrans (TOM) |  |  | Accessible service. SIA 5 | M4b
PTS5 | Public Transport Services | Develop Area bus forums/PT forums, alongside CC consultation | ZetTrans (PSM) |  |  | Needs-based service delivery, user involvement. SIA 1-5 | M8a
PTS7 | Monitoring | Continue to monitor usage of all services, considering more demand responsive provision, where possible | ZetTrans (PSM) |  |  | To effectively match level of provision to demand. ECON 1 | KPI4a and b, KPI5, M1, M5a
PTF1 | Fares and Ticketing | Continue to specifiy fare levels within bus service contracts, with levels reviewed annually (cost and accessiblity) | ZetTrans (PSM) |  |  | Economic and accessible service. ECON 5, SIA 1-5 | KPI4a, M1, M5a, M8a
PTF2 | Fares and Ticketing | Continue to provide free public transport for elderly and disabled, in accordance with national transport concessionary scheme and 16-18 year old in accordance with SG concessionary scheme | ZetTrans (PSM) |  |  | Accessiblity. SIA 1-5 | KPI4a, M1, M5a, M8a
PFT3 | Fares and Ticketing | Lobby for extension of scheme to community transport | ZetTrans (HT) |  |  | Accessiblity. SIA 1-5 | KPI4a, M1, M5a, M8a
PTF4 | Fares and Ticketing | Multi-ticket options/ development of new ticketing initiatives, such as introduction of 'Shetland Pass' primarily aimed at visitors to Shetland | ZetTrans (PSM) |  |  | Accessiblity. ECON 7, SIA 1-5 | KPI4a, M1, M5a, M8a
PTI1 | Information, infrastructure, facilities | Continue to provide real-time information for services at Viking and consider new locations | ZetTrans (PSM) |  |  | Accessibility. ECON 7, SIA 1-5 | KPI4a, M1, M5a, M8a
PTI2 | Information, infrastructure, facilities | Publication and circulation of timetables and user guides (hardcopy and web) | ZetTrans (PSM) |  |  | Increase ease and usage of PT system. ECON 7, SIA 1-5 | KPI4a, M1, M5a, M8a
PTI3 | Information, infrastructure, facilities | Continue to operate and maintain Viking, inc. information, left luggage and smaller parcels | ZetTrans (TOM) |  |  | Accessibility. ECON 7, SIA 1-5 | KPI4a, M1, M5a, M8a
PTI4 | Information, infrastructure, facilities | Continue to provide and maintain bus shelters, inc. timetable cases, where appropriate | ZetTrans (TOM) |  |  | Accessibility. ECON 7, SIA 1-5 | KPI4a, M1, M5a, M8a
PTI5 | Information, infrastructure, facilities | Appropriate timetable information and waiting facilities at key interchange points | ZetTrans (PSM) |  |  | Accessibility. ECON 7, SIA 1-5 | KPI4a, M1, M5a, M8a
PTI6 | Information, infrastructure, facilities | Meaures to increase amenity of PT waiting facilities, increase feelings of safety | ZetTrans (TOM), community groups |  |  | Accessibility. ECON 7, SIA 1-5 | KPI4a, M1, M5a, M8a
EPM6 | Alternative Fuels | Undertake study into use of alternative fuels (including biofuels) and energy conservation measures for the Council's fleet of vehicles and vessels | ZetTrans (PSM) and SIC |  |  | Reduction in carbon emissions. ENV 1 | KPI3